VITALITY WEIGHT MANAGEMENT PROGRAM

Proposal in Response to Sedgwick County RFP #26-0028

Employee Ancillary Benefits — Weight Loss / Weight Management Program

Submitted to:

Tammy Culley, Purchasing Agent

Sedgwick County Purchasing Department

100 N. Broadway, Suite 610

Wichita, KS 67202

purchasing@sedgwick.gov

Submitted by (Prime Contractor):

Eric Hargrave, CEO

Hargrave Innovative Solutions (HIS)

ericd@hisolution.org · 601-238-4186

In partnership with:

Love Clinic MedSpa · Vanntastic Solutions · The COLLABORATIVE Advocate Foundation

Date of submission: June 2, 2026

Submission deadline acknowledged: 1:45 PM CDT, June 2, 2026

Addenda acknowledged:

- Addendum #1 (as issued) — signed acknowledgment in Appendix C

- Addendum #2 (issued May 22, 2026 by Tammy Culley, Purchasing Agent) — signed acknowledgment in Appendix C

TABLE OF CONTENTS

- Cover Letter

- Executive Summary

- Team and Organizational Qualifications

- Understanding of the County's Needs

- Program Design — Vitality Comprehensive Weight Management

- Technology Platform

- Implementation Plan

- Pricing Model and Return on Investment

- Reporting and Performance Metrics

- References and Past Performance

- Compliance, Insurance, and Certifications

- Appendices

Section 1 — Cover Letter

To: Ms. Tammy Culley, Purchasing Agent, Sedgwick County

Dear Ms. Culley,

On behalf of Hargrave Innovative Solutions and our three named subcontractors — Love Clinic MedSpa, Vanntastic Solutions, and The COLLABORATIVE Advocate Foundation — I am pleased to submit our proposal in response to RFP #26-0028, Employee Ancillary Benefits — Weight Loss / Weight Management Program.

We acknowledge receipt of Addendum #1 and Addendum #2 (issued May 22, 2026), and signed acknowledgments are included in Appendix C of this proposal.

Our team is local. Three of our four partners are based in Wichita; the fourth is a U.S. Army retiree with deep public-sector implementation experience. We understand Sedgwick County not as a logo on a contract but as our neighbors, our friends, and our families. Several of our partners' family members are on the County medical plan today.

We have read Addendum #2 carefully. The County's disclosure that 373 members are currently on GLP-1 therapy — with 705 members having started a GLP-1 in just the past twelve months — tells us that the County is already absorbing a significant pharmacy-cost burden, and the ~47% twelve-month attrition rate tells us that prior authorization alone is not converting that spend into outcomes. Our proposal is designed around capturing that gap.

We believe this proposal represents the best value available to Sedgwick County under RFP #26-0028:

- We are the only respondent with a fully integrated four-partner structure that combines prescribing clinical capability (Dr. Chela Love, DNP), wellness coaching and behavioral engagement (Dr. J. Michelle Vann), digital platform and engagement systems (Dr. Terry D. Flood, DHA, EdD), and disciplined prime-contractor government compliance (Hargrave Innovative Solutions).

- Our proposed program model captures the approximately $2.09 million per year in managed-GLP-1 savings already addressable within the County's current 373-member GLP-1 cohort, while also serving the broader 1,525 at-risk adult population with evidence-based lifestyle and clinical pathways.

- Our technology platform is purpose-built to integrate with — not replace — UnitedHealthcare (TPA), OptumRx (PBM), and Rally (current wellness platform). We coordinate; we do not displace.

- We are HIPAA-compliant, prepared to execute the County's standard Business Associate Agreement at award, and willing to discuss at-risk performance-based pricing tied to engagement, GLP-1 utilization, and cost savings — the three KPIs the County named in the Addendum.

All communication regarding this proposal will route through me as the Prime Contractor's authorized representative. I am personally accountable for our team's performance under any awarded contract.

Thank you for your consideration. We look forward to the opportunity to serve Sedgwick County.

Respectfully submitted,

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Eric Hargrave, CEO

Hargrave Innovative Solutions (Prime Contractor)

ericd@hisolution.org · 601-238-4186

Section 2 — Executive Summary

2.1 The three-sentence thesis

Sedgwick County is already spending approximately $5.15M per year on unmanaged GLP-1 medications for 373 employees and dependents, with a ~47% twelve-month attrition rate that demonstrates prior authorization alone is not working. Vitality's integrated clinical-plus-coaching managed-care protocol can capture approximately $2.09M per year of that spend in Year 1 — nearly funding the entire program — while delivering a sustainable lifestyle change pathway for the broader 1,525 at-risk adult population. We build with, not against, UnitedHealthcare, OptumRx, and Rally; we displace no existing vendor; and we are the only respondent purpose-built for the four-partner program design model the County asked for.

2.2 What Vitality is

Vitality is a comprehensive, virtual-only weight management program designed for self-insured public-sector employers. The program combines:

- Three evidence-based clinical pathways (Lifestyle, GLP-1-Managed, and Surgical-Coordinated), each anchored in published evidence (NIH/DPP, STEP Trials, LOOK AHEAD, RAND).

- A 5-phase member journey (onboarding, baseline, intensive intervention, maintenance, graduation) overseen by Dr. Chela Love, DNP and her clinical team at Love Clinic MedSpa.

- A behavioral coaching engine led by Dr. J. Michelle Vann, with weekly check-ins, lifestyle accountability, and family/youth program extensions.

- A digital Progressive Web App platform (no app-store install required) built and operated by Dr. Terry D. Flood's team at The COLLABORATIVE Advocate Foundation, with FHIR/HL7 integration, persistent-memory AI coaching, and HIPAA-grade security.

- Prime contractor administration by Hargrave Innovative Solutions, providing government contract management, compliance oversight, reporting coordination, and single-point accountability.

2.3 Why Vitality wins on the County's three named KPIs

The County named three KPIs in Addendum #2, in this order:

- Member engagement — Vitality's VITA AI persistent-memory advisor remembers every prior conversation with each member and resumes context across sessions. Combined with Dr. Vann's weekly behavioral cadence, the program is designed to sustain engagement over 12–24 months, not just at signup.

- Proper use of GLP-1s — Dr. Love's structured titration protocol, OptumRx fill-history reconciliation, and side-effect management directly address the attrition pattern visible in the County's 705 → 373 cohort data.

- Cost savings — modeled Year-1 economic opportunity of approximately $3.05M (the $2.09M GLP-1 capture plus $675K medical and $282K productivity savings) against a $1.71M Year-1 program cost.

2.4 Why Vitality wins on the County's procurement preferences

| County preference (from Addendum #2 and RFP) | Vitality alignment |
| --- | --- |
| Comprehensive solution, not administration | Four-partner integrated team designs the program end-to-end |
| Support-focused, not compliance-focused | Coaching-plus-clinical wraparound; no PBM-style claim denial |
| Virtual delivery only | PWA-native platform; no onsite costs |
| Adults 18+ | Adult-only clinical scope; simplified pathway |
| Integration with existing UHC / OptumRx / Rally | Coexistence architecture; FHIR/HL7-ready |
| Either prescribing or coaching clinical model acceptable | Vitality offers both inside a single program |
| KPI focus: engagement, GLP-1 use, cost savings | Native dashboard and quarterly report structure aligned to these three metrics |

Section 3 — Team and Organizational Qualifications

Vitality is delivered by a four-partner team. Three of four partners are headquartered in Wichita; the fourth is a U.S. Army retiree with extensive federal and public-sector implementation experience. The team is purpose-built for the integrated clinical-plus-coaching-plus-platform model the County asked for.

3.1 Prime Contractor — Hargrave Innovative Solutions (HIS)

Principal: Eric Hargrave, CEO — ericd@hisolution.org · 601-238-4186

Role under this contract: Prime contractor with single-point accountability to Sedgwick County. Responsibilities include government contract management, compliance oversight, reporting coordination, administrative support, financial management, subcontractor coordination, performance management, and BAA execution.

Relevant experience: Health-tech platform delivery and multi-vendor IT consulting. Active prime contractor with public-sector engagements. References available upon request.

3.2 Clinical Lead — Love Clinic MedSpa

Principal: Dr. Chela Love, DNP — chelalove@loveclinicmedspa.com · 316-669-4770

Location: 214 S Rock Rd, Suite 101, Wichita, KS 67207 · www.loveclinicmedspa.com

Role under this contract: Medical oversight, GLP-1 protocol design and supervision, prescribing authority for in-program GLP-1 management pathway, clinical governance, member medical care.

Relevant experience: Active clinical practice in Wichita with substantial GLP-1 patient panel. Active Kansas DNP licensure. References available from current patient panel and referring providers, subject to HIPAA authorization.

3.3 Wellness Lead — Vanntastic Solutions

Principal: Dr. J. Michelle Vann, Dcc, ThD, MS — 316-350-2601 · www.jmichellevann.com

Role under this contract: Wellness coaching, behavioral engagement, lifestyle accountability, weekly member check-in cadence, family and youth programming extensions for members with dependents.

Relevant experience: Recognized public speaker (TEDx). Substantive work in youth and family wellness programming and community-based health initiatives in the Wichita area. Active speaker and content creator on lifestyle accountability and behavioral health.

3.4 Platform and Data Lead — The COLLABORATIVE Advocate Foundation

Principal: Dr. Terry D. Flood, DHA, EdD — 254-319-8460

Role under this contract: Digital platform and app development, participant engagement systems, reporting and analytics, healthcare data architecture, FHIR/HL7 integration, security and HIPAA technical controls.

Credentials: DHA, EdD, MSIOP, MSW(c), MSL, MSCJPP, MSHRM, MSIS(c), BHA, CHW-I

Relevant experience: U.S. Army retiree with extensive public-sector implementation background. Active Secret-level clearance. PMP-eligible. Specialization in healthcare data standards (FHIR, HL7), population health analytics, and federal-grade systems implementation.

3.5 Subcontracting structure

Hargrave Innovative Solutions is the sole Prime Contractor. Love Clinic MedSpa, Vanntastic Solutions, and The COLLABORATIVE Advocate Foundation are named subcontractors. All four partners have agreed to the team structure and have authorized this proposal. The County contracts only with HIS; HIS holds three back-to-back subcontract agreements that flow down all material terms (including HIPAA / BAA, insurance, performance standards, and termination provisions) from the County contract.

This structure provides the County with:

- A single point of contact (Eric Hargrave) for all contractual, performance, and escalation matters

- Single-source billing and accounts payable

- Disciplined compliance management through HIS's prime-contractor administrative function

- Clear delineation of clinical responsibility (Dr. Love), wellness responsibility (Dr. Vann), and technology responsibility (Dr. Flood)

Section 4 — Understanding of the County's Needs

4.1 Population baseline (from Addendum #2)

The County disclosed the following figures in Addendum #2 (issued May 22, 2026). Vitality has structured the entire proposal around these numbers as authoritative.

| Metric | Value |
| --- | --- |
| Total members enrolled on County medical plans (all ages) | 5,871 |
| Eligible adult population (employee + dependents age 18+) | 4,213 |
| Female share of population | 53% |
| Currently on GLP-1 medication | 373 (6.3% of enrolled, 8.9% of adults) |
| Used GLP-1 in past 12 months | 705 (12.0% of enrolled, 16.7% of adults) |
| BMI ≥ 30 count | Unavailable from carrier |
| CDC PLACES county obesity prevalence | 36.2% |
| Modeled at-risk adult population | ~1,525 (4,213 × 36.2%) |
| TPA | UnitedHealthcare (self-insured Group #902769) |
| PBM | OptumRx |
| Broker of record | IMA |
| Current wellness platform | Rally (via UHC) |
| Incumbent weight-management vendor | None |
| Required service delivery | Virtual only |

4.2 The GLP-1 utilization picture

The single most operationally significant disclosure in Addendum #2 is the GLP-1 utilization data. We interpret it as follows:

(a) Current GLP-1 spend is substantial and unmanaged. At the conservative RAND 2023 figure of $13,800 per unmanaged GLP-1 patient per year, the 373 current GLP-1 members represent approximately $5.15 million in annual pharmacy cost to the County's medical plan. This spend is occurring with no clinical oversight beyond standard PBM prior authorization.

(b) The 47% twelve-month attrition rate is the diagnostic signal. 705 members started a GLP-1 in the past twelve months, but only 373 are on therapy today. The 332-member differential — approximately 47% of starters — represents members who paid in (through pharmacy claims) but did not achieve sustained outcomes. This attrition pattern is consistent with published GLP-1 real-world adherence data showing 40–55% discontinuation within twelve months in unmanaged settings, driven by side effects (nausea, fatigue), lack of titration support, and absence of behavioral coaching.

(c) The savings opportunity is concrete and addressable. RAND's 2023 conservative figure for the cost differential between unmanaged and managed GLP-1 therapy is $5,600 per patient per year ($13,800 − $8,200). Applied to the 373 current GLP-1 members, the managed-protocol savings opportunity is approximately $2.09 million per year. Migrating the cohort to a managed protocol does not require a single new prescription or any change to OptumRx's formulary — it requires only that the existing 373 members receive structured clinical oversight, titration support, side-effect management, and behavioral coaching.

4.3 Current gap analysis

The Addendum disclosed: *"Current cost containment is tied to prior authorization program with PBM."* The County has identified this as insufficient and has stated its preference for *"a broader support-focused program centered around outcomes, health coaching participation, and sustainable lifestyle changes."*

We share the County's diagnosis. Prior authorization gates approval at the moment of prescription but does not address:

- Side-effect management during titration (the primary driver of 47% attrition)

- Behavioral coaching to support sustained dietary and activity changes

- Lifestyle accountability and engagement over 12–24 months

- Coordination across members' broader care team (PCP, OB-GYN, mental health, etc.)

- Outcome measurement and reporting to the County

Vitality is designed to fill exactly this gap, while preserving OptumRx's PBM role and UnitedHealthcare's TPA role.

4.4 What the County asked for, in the County's own language

| County requirement (Addendum #2) | Vitality response section |
| --- | --- |
| "Recommend and design a comprehensive solution" | Section 5 (Program Design) |
| "A broader support-focused program centered around outcomes" | Section 5.4 (Behavioral Engagement) + 5.6 (GLP-1 Managed Protocol) |
| "Integration is preferred, if available. TPA = UHC, PBM = OptumRx" | Section 6 (Technology Platform) |
| "Continued member engagement, proper use of GLP-1s, and cost savings" | Section 9 (Reporting and KPIs) + Section 8 (ROI) |
| "Virtual support only" | Section 5 (Program Design) and Section 6.1 (PWA Architecture) |
| "18 and over" | Section 5 (adult-only clinical pathway) |
| "Either model is acceptable" (in-house prescriber OR NBHWC coach with member's prescriber) | Section 5.6 (dual-pathway design) |
| "Network access = integration with existing medical plan ecosystem" | Section 6 (Technology Platform) |

Section 5 — Program Design: Vitality Comprehensive Weight Management

5.1 Program philosophy

Vitality is built on five principles:

- Member-centric, not vendor-centric. Every design decision starts from the member's job-to-be-done.

- Evidence-based. Every clinical recommendation cites the underlying study (DPP, STEP, LOOK AHEAD, RAND, NIH).

- Integration-first. We coexist with the County's existing UHC, OptumRx, and Rally relationships. We do not replace them.

- Support-focused. We meet the County's stated preference: coaching and clinical wraparound, not compliance enforcement.

- Outcomes over activity. Every dashboard leads with the three KPIs the County named.

5.2 Member journey — the 5-phase clinical protocol

Every Vitality member moves through five phases. Each phase has defined entry and exit criteria, a clinical owner, and a measurable outcome.

| Phase | Duration | Owner | Outcome |
| --- | --- | --- | --- |
| 1. Onboarding | 1–2 weeks | Vitality coaching | Identity verified, employer eligibility confirmed, consent collected, baseline survey complete |
| 2. Clinical baseline | 2–4 weeks | Dr. Love (Clinical) | Medical baseline, BMI, A1C, blood pressure, comorbidity inventory, pathway assignment |
| 3. Intensive intervention | 12–26 weeks | Dr. Love + Dr. Vann | Pathway-specific intervention (lifestyle, GLP-1, surgical-coordinated); weekly coaching cadence; biweekly clinical check |
| 4. Maintenance | 26–52 weeks | Dr. Vann (Behavioral) | Reduced cadence (biweekly to monthly); habit consolidation; outcome stabilization |
| 5. Graduation | Ongoing | Self-directed with quarterly check-in | Member graduates to alumni program with quarterly touchpoints; clinical and engagement data continue to feed reporting for the savings carryover model |

5.3 Three clinical pathways

Members are assigned to one of three pathways during Phase 2 (Clinical baseline), based on Dr. Love's clinical assessment, member preference, and clinical guideline match.

Pathway A — Lifestyle Intervention (estimated 72% of enrolled members)

- Evidence base: NIH/DPP Trial (58% reduction in type 2 diabetes progression at 5–10% weight loss)

- Components: structured nutrition coaching, activity tracking, behavioral group sessions led by Dr. Vann, weekly check-ins

- Clinical cadence: quarterly Dr. Love review

- Cost component: lifestyle baseline ($3,200/member/year all-in)

Pathway B — GLP-1 Managed Care (estimated 20% of enrolled members)

- Evidence base: STEP-1, STEP-2, STEP-3 trials (15–17% body weight reduction at 68 weeks)

- Components: GLP-1 prescription, structured titration, side-effect management, monthly clinical visits, weekly coaching, OptumRx fill-history reconciliation

- Clinical cadence: monthly Dr. Love visit during titration; quarterly during maintenance

- Member can elect: in-program prescribing (Dr. Love) OR coaching-only support with member's existing prescriber (per Addendum #2 confirmation that either model is acceptable)

Pathway C — Surgical-Coordinated (estimated 8% of enrolled members)

- Evidence base: LOOK AHEAD Trial (sustained 7–8% loss at 4 years with intensive lifestyle); bariatric surgery outcomes literature

- Components: pre-surgical clinical evaluation, post-surgical lifestyle support, coordination with member's chosen surgical center, long-term behavioral coaching

- Clinical cadence: aligned with surgical center protocol; Vitality provides wrap-around support

5.4 Behavioral engagement model

Dr. Vann's behavioral engagement model is the engine that sustains member engagement — the County's #1 KPI.

- Weekly check-in cadence during Phase 3 (intensive intervention), via the Vitality PWA, with structured prompts and a coaching response within 24 hours.

- Biweekly group sessions during Phase 3 and Phase 4, virtual cohort format, 8–12 members per cohort, facilitated by Dr. Vann or a licensed coach under her supervision.

- Family and youth programming extensions for members with dependents — addressing the household environment that drives sustainable weight management.

- Automated escalation for any member who does not check in for 14 days, routed to a human coach for outreach.

- Engagement scoring for the dashboard, surfaced to the County in quarterly reports.

5.5 VITA AI persistent-memory advisor

VITA is Vitality's AI coaching assistant, embedded in the member portal and the employer dashboard. VITA is differentiated from generic AI chatbots by three properties:

- Persistent memory. Every member conversation is stored. VITA resumes context on every new session — there is no "starting over." A returning member sees a "Resuming — X prior exchanges" badge on their portal.

- Live clinical context. VITA receives the member's current weight, BMI, GLP-1 status, active care plan phase, recent weight trend, and achieved milestones with every message. Responses are anchored to the member's real situation, not generic content.

- Evidence-cited responses. VITA's clinical answers cite specific studies (DPP, STEP, LOOK AHEAD, RAND). This is a deliberate design choice for an RFP-evaluator audience as well as for clinical defensibility.

VITA operates in two modes: a warm, Dr. Love–voiced member mode, and an analytical, ROI-focused employer mode for the County dashboard. Both modes share the same persistent-memory architecture.

5.6 The GLP-1 managed-care protocol — the headline differentiator

This is the operational answer to the $2.09M Year-1 savings opportunity. The protocol has six components:

- Initial clinical evaluation by Dr. Love for every member entering Pathway B. Establishes baseline metrics, comorbidities, contraindications, and titration plan.

- Structured titration over 12–16 weeks with proactive side-effect management. Members are contacted on day 3, day 7, day 14, and weekly thereafter during titration to surface and address side effects before they cause discontinuation. This is the single most important intervention against the 47% attrition pattern.

- OptumRx fill-history reconciliation. Vitality receives weekly fill-history feeds from OptumRx and reconciles them against expected fills. Members who miss a fill receive coaching outreach within 48 hours.

- Behavioral coaching from Dr. Vann's team throughout titration and maintenance. Members on GLP-1 receive structured nutrition support, activity coaching, and sleep/stress modules — the lifestyle scaffolding that makes the medication work.

- Coordination with member's existing prescriber (if the member chooses to remain with their PCP rather than have Dr. Love prescribe). Vitality acts as the supporting coaching and reporting layer; the member's PCP retains prescribing authority. Per Addendum #2, the County has confirmed this model is acceptable.

- Monthly clinical visits during titration; quarterly thereafter. Dr. Love (or a credentialed clinician on her team) maintains direct medical oversight throughout the member's GLP-1 course.

The protocol directly targets the 47% attrition rate visible in the County's 705-to-373 cohort transition. If Vitality reduces twelve-month attrition from 47% to 25% — a conservative target relative to managed-GLP-1 published outcomes — the County retains an additional ~155 members on effective therapy in Year 1, with corresponding compounding outcomes and savings.

Section 6 — Technology Platform

6.1 PWA architecture

The Vitality member experience is delivered as a Progressive Web Application (PWA). This means:

- No app-store install required. Members access the program from any modern web browser on any device — phone, tablet, laptop, desktop. The PWA supports add-to-home-screen on iOS and Android for native-app-style access without the friction of an app-store flow.

- Offline capability. Members can log weight, complete daily check-ins, and review coaching materials offline; data syncs when connectivity returns.

- Push notifications on Android and modern iOS, for coaching prompts, medication reminders, and weekly check-in nudges.

- Accessibility: WCAG 2.1 AA compliance, Section 508 compliance, screen-reader support, keyboard navigation, high-contrast mode.

The platform stack is React 19 + TypeScript on the front end, Express 5 on the API server, PostgreSQL with Drizzle ORM for the database, and a Claude AI (Anthropic) integration for the VITA assistant. All software is built and maintained by Dr. Flood's team at The COLLABORATIVE Advocate Foundation.

6.2 Integration with UnitedHealthcare (TPA)

UnitedHealthcare is Sedgwick County's TPA on the self-insured plan (Group #902769). Vitality integrates with UHC across three surfaces:

- Eligibility feed: SFTP or API-based daily roster sync from UHC's eligibility files. Establishes the eligible adult population (4,213 per Addendum #2) and supports automated enrollment validation.

- Claims data feed: Monthly de-identified claims extract under BAA, used for outcome measurement (claims-cost trend, hospital and ER utilization for the at-risk cohort).

- FHIR R4 read access (if available from UHC's API gateway): supports real-time member clinical context for VITA and Dr. Love's clinical team.

Integration timeline: 30–45 days from contract execution, dependent on UHC IT scheduling.

6.3 Integration with OptumRx (PBM)

OptumRx is Sedgwick County's PBM. Vitality integrates across two surfaces:

- GLP-1 authorization status feed: read-only access to OptumRx prior-authorization decisions for members enrolled in Vitality. This allows Dr. Love's clinical team to know which members have current GLP-1 authorization without manually contacting members.

- Fill-history feed: weekly extract of GLP-1 fill events for enrolled members. Drives the fill-reconciliation process described in Section 5.6.

We do not request prescribing authority within OptumRx, do not modify the formulary, and do not change any prior-authorization rules. Vitality's role is observational and coordinative.

Integration timeline: 30–45 days from contract execution.

6.4 Coexistence with Rally

Rally is the County's current member-engagement platform, provided through UHC. Vitality coexists with Rally rather than replacing it. Our integration model:

- Single-sign-on hand-off. Members can launch Vitality from Rally with a one-click SSO flow (Azure AD / SAML 2.0).

- Engagement data exchange. Vitality engagement metrics (check-ins, coaching touchpoints) can be exported to Rally to roll up into the County's broader wellness dashboard.

- No duplication of general-wellness content. Rally remains the source of truth for general wellness (gym reimbursement, biometric screenings, mental health). Vitality is the source of truth for weight management and GLP-1 utilization specifically.

6.5 Single sign-on and identity

Vitality supports the following SSO and identity providers:

- Microsoft Entra ID / Azure AD (SAML 2.0 and OIDC) — recommended for the County's environment

- Okta (SAML 2.0 and OIDC)

- Google Workspace (OIDC)

- City/County LDAP (legacy support)

- Multi-factor authentication enforced for all administrative and clinical users

- Self-service password reset for members; SSO bypass for members who prefer email/password

6.6 Security, HIPAA, and data governance

- HIPAA compliance at the technical, administrative, and physical levels. Business Associate Agreement will be executed at contract award.

- Encryption at rest (AES-256) and in transit (TLS 1.3).

- Role-based access control. Clinical roles (Dr. Love and her team), coaching roles (Dr. Vann and her team), administrative roles, and County reviewer roles each have defined access scopes.

- Audit logging of every clinical data access, retained for 7 years per HIPAA.

- Data residency in U.S.-based cloud infrastructure with SOC 2 Type II certification.

- 42 CFR Part 2 readiness if the County identifies any substance-use-disorder data flows that require it.

- De-identification for all aggregate reports to the County (HIPAA Safe Harbor or Expert Determination method, depending on cohort size).

- Member access and portability rights under HIPAA: members can export their full Vitality record at any time.

Section 7 — Implementation Plan

7.1 90-day stand-up timeline

| Week | Workstream | Milestone |
| --- | --- | --- |
| 1–2 | Contracting | Contract execution, BAA execution, kickoff meeting with County procurement, HR, and Risk Management |
| 1–3 | Technical | UHC eligibility-feed connection initiated, OptumRx fill-history feed initiated, SSO configuration with County IT |
| 2–4 | Clinical | Dr. Love finalizes program clinical protocols, GLP-1 titration playbook, side-effect management algorithms |
| 3–5 | Coaching | Dr. Vann finalizes coaching curriculum, weekly cadence templates, group-session structure |
| 4–6 | Platform | Vitality PWA tenanted for Sedgwick County; County branding applied; SSO live in test environment |
| 5–7 | Compliance | HIPAA risk assessment complete; security review with County IT |
| 6–9 | Launch readiness | UAT with a 10-member County pilot cohort; integration end-to-end validation |
| 9–10 | Communication | Member-facing communication plan executed (email, intranet, printed materials in County offices) |
| 10–12 | Soft launch | Open enrollment begins; first 100 members onboarded; daily standups with County |
| 13 | Full launch | Program at full operational capacity |

7.2 Risk register

| Risk | Mitigation |
| --- | --- |
| UHC eligibility-feed delay | Manual roster upload as bridge; standard UHC integration is well-precedented |
| OptumRx feed delay | Member self-report of GLP-1 status as bridge; manual reconciliation until automated feed live |
| Low initial enrollment | Targeted communication plan; incentive structure in coordination with County HR |
| Member skepticism of new program | Dr. Love's local Wichita presence; testimonials from Phase 1 cohort; transparent reporting on outcomes |
| County turnover during contract | Single-point-of-contact through HIS Prime; documented runbooks; quarterly executive briefings to ensure continuity across personnel changes |

Section 8 — Pricing Model and Return on Investment

8.1 PEPM (per-employee-per-month) pricing structure

Vitality offers a blended PEPM pricing model that scales with the County's enrolled member count and the actual mix of clinical pathways used. The blended PEPM range is $476–$525 per enrolled member per month, depending on the GLP-1 mix.

The pricing is constructed bottoms-up from operational cost components:

| Component | $/member/month |
| --- | --- |
| Coaching (Dr. Vann's team + VITA AI) | $55 |
| Platform & analytics (CAF technology infrastructure) | $45 |
| Administration, compliance, and BAA management (HIS) | $30 |
| Clinical oversight (Dr. Love, blended across pathways) | $45 lifestyle / $130 GLP-1 / $75 surgical |
| GLP-1 medication (at negotiated specialty rate, when applicable) | $930 for the 20% on the GLP-1 pathway |
| Operator margin (20%) | Variable |

At a representative 20% GLP-1 mix, the blended all-in PEPM is approximately $476. At a 30% GLP-1 mix, it rises to approximately $525.

8.2 Lifestyle pathway baseline cost

For members on Pathway A (Lifestyle), the all-in annual cost is $3,200 per member per year ($267/month). This includes coaching, platform, administration, and clinical oversight, but excludes medication (none required on this pathway).

8.3 Year-1 program cost at target enrollment

At our target enrollment of 534 members (35% of the 1,525 modeled at-risk adult population), the Year-1 program cost at the lifestyle baseline is $1,708,800.

This figure is conservative — it assumes all enrollees are on the lifestyle pathway. At the realistic ~20% GLP-1 mix, the actual Year-1 cost is approximately $2.55M–$2.80M (the higher figure reflects the GLP-1 medication cost that is otherwise being absorbed by the pharmacy plan today).

8.4 Return on Investment — the headline economic case

8.4.1 The GLP-1 capture

The single largest ROI driver is the migration of the County's existing 373 GLP-1 members from unmanaged to managed therapy.

- Current spend: 373 × $13,800 = $5,147,400 per year (RAND 2023 unmanaged figure)

- Managed spend: 373 × $8,200 = $3,058,600 per year (RAND 2023 managed figure)

- Annual savings opportunity: $2,088,800

This is not a hypothetical population; it is the County's actual current cohort, disclosed in Addendum #2.

8.4.2 Lifestyle and clinical savings

Modeling the broader at-risk population at 35% enrollment (534 members), 68% clinical threshold achievement (NIH/DPP), and per-success savings of $2,639 ($1,861 medical from CDC/CMS 2023 + $778 productivity from RAND, 2.73 days × $285/day):

- Successful members: 534 × 68% = 363

- Annual medical savings: 363 × $1,861 = $675,543

- Annual productivity savings: 363 × $778 = $282,414

- Subtotal: $957,957 per year

8.4.3 Total Year-1 economic opportunity

- GLP-1 capture: $2,088,800

- Lifestyle + clinical: $957,957

- Total: $3,046,757 per year

Against a Year-1 program cost of $1,708,800 (lifestyle baseline) or up to ~$2.80M (with realistic GLP-1 mix), the County's net Year-1 benefit is $240K–$1.34M in Year 1, and grows through Years 2–5 with graduate-savings carryover.

8.4.4 Multi-year ROI projection

Using a conservative graduate-savings carryover model (85% YoY retention of savings from members who hit clinical threshold, capped at a 3-year carry tail per DPP follow-up data):

| Year | Cumulative ROI ratio |
| --- | --- |
| Year 1 | 0.56x |
| Year 3 | 1.01x (break-even) |
| Year 5 | 1.32x |

The headline industry benchmark (Harvard meta-analysis 2010: $3.27 return per $1 invested in workplace wellness) is the upper bound — we deliberately under-promise relative to that benchmark.

8.5 At-risk performance pricing (optional structure)

If the County prefers, Vitality is willing to convert a portion of the PEPM (typically 10–20%) to an at-risk performance fee tied to the three County KPIs: member engagement (measured by 90-day active rate), proper GLP-1 use (measured by twelve-month adherence), and cost savings (measured by year-over-year cost trend versus a no-program baseline).

We are open to structuring this as either a fee withhold (released on performance) or a bonus (paid above PEPM on outperformance). The specific structure is negotiable at contract.

Section 9 — Reporting and Performance Metrics

9.1 KPI alignment with County priorities

Vitality's reporting framework is structured around the three KPIs the County named in Addendum #2, in this order:

KPI 1 — Continued member engagement

- 30/60/90-day active rate

- Weekly check-in completion rate

- Coaching touchpoint volume per member per month

- Time-to-disengagement (days from last activity)

- Cohort retention curves

KPI 2 — Proper use of GLP-1 medications

- Twelve-month adherence rate on GLP-1 pathway

- Titration completion rate

- Side-effect-driven discontinuation rate (vs. unmanaged baseline)

- Fill-reconciliation gap rate

- Clinical-visit attendance rate

KPI 3 — Cost savings

- Year-over-year medical cost trend for enrolled cohort vs. matched no-program cohort

- GLP-1 PMPY (per member per year) for enrolled vs. unenrolled GLP-1 users

- Productivity savings estimate (RAND model)

- Cumulative program ROI ratio

9.2 Reporting cadence

| Audience | Cadence | Format |
| --- | --- | --- |
| County Risk Management and HR | Monthly | Operational dashboard (PDF + live web link) |
| County executive (County Manager, Finance) | Quarterly | Executive summary with KPI trend, financial summary, action items |
| Board of County Commissioners | Annual | Outcomes report with year-over-year comparison |
| County IT and security | Quarterly | Security and compliance review |
| Broker of record (IMA) | Quarterly | Aligned with executive summary; IMA-facing economic detail |

9.3 Dashboard architecture

The Vitality employer dashboard is accessible via the County's existing SSO infrastructure (Azure AD). Authorized County users (HR, Risk Management, Finance, IT, leadership) see a real-time view of:

- Population baseline (4,213 adults, 5,871 enrolled — refreshed from UHC eligibility feed)

- Current enrollment by pathway

- KPI performance against targets

- GLP-1 utilization (pipeline view: past-year users → currently authorized → active on medication → goal achieved)

- ROI projection (live, with multi-year scenarios)

- Engagement alerts (members at risk of disengagement)

- VITA AI Analytics Advisor (employer mode) for natural-language queries

All de-identified aggregate exports are downloadable as CSV for ingestion into the County's preferred BI tooling (Power BI, Tableau, or equivalent).

Section 10 — References and Past Performance

References are organized by team competency. Detailed reference letters and performance documentation are available upon request from the Sedgwick County Purchasing Department.

| Competency domain | Lead | Reference scope |
| --- | --- | --- |
| Prime contractor and government compliance | Eric Hargrave, HIS | Active prime-contractor engagements; public-sector and enterprise health-tech implementations. References available on request. |
| Clinical weight management | Dr. Chela Love, DNP, Love Clinic MedSpa | Active clinical practice in Wichita; GLP-1 patient panel. References available from current patient panel and referring providers, subject to HIPAA authorization. |
| Wellness coaching and behavioral engagement | Dr. J. Michelle Vann, Vanntastic Solutions | Public speaking (TEDx); community-based wellness programming; youth and family wellness work in the Wichita area. References available on request. |
| Digital platform, engagement systems, and data | Dr. Terry D. Flood, DHA, EdD, COLLABORATIVE Advocate Foundation | U.S. Army retiree with extensive public-sector implementation background. Active Secret-level clearance. PMP-eligible. FHIR/HL7 integration work. References available on request, subject to clearance constraints. |

Section 11 — Compliance, Insurance, and Certifications

11.1 HIPAA and Business Associate Agreement

Hargrave Innovative Solutions, as Prime Contractor, will execute the County's standard Business Associate Agreement at contract award. All three subcontractors (Love Clinic MedSpa, Vanntastic Solutions, The COLLABORATIVE Advocate Foundation) will execute back-to-back BAAs with HIS that flow down all material HIPAA terms from the County's BAA. We are prepared to execute the County's standard template, or to negotiate any County-required modifications.

11.2 Insurance and bonding

The HIS Prime Contractor team carries:

- Commercial general liability

- Professional liability (errors and omissions)

- Cyber liability

- Workers' compensation (where applicable)

Specific coverage levels can be tailored to the County's requirements. If the County requires performance or payment bonding, HIS is prepared to provide bonding through an established surety relationship at the levels specified in the contract.

11.3 Sedgwick County procurement compliance

All communication regarding RFP #26-0028 is directed exclusively through the Sedgwick County Purchasing Department (Tammy Culley, Purchasing Agent · 100 N. Broadway, Suite 610, Wichita, KS 67202 · purchasing@sedgwick.gov). The Vitality team will not contact County employees, department heads, evaluation committee members, or elected officials regarding this solicitation.

The HIS team and all named subcontractors comply with the County's standard procurement integrity provisions, including no gifts, no inducements, and full disclosure of any actual or perceived conflicts of interest. None are known to us at the time of this submission.

If awarded, the Vitality team is prepared to execute the County's standard contract template, including all standard termination, audit, indemnification, and dispute-resolution provisions.

Section 12 — Appendices

Appendix A — Strategic Analysis of RFP #26-0028 Addendum #2

This appendix documents the strategic conclusions the Vitality proposal team drew from Addendum #2, issued May 22, 2026 by Tammy Culley, Purchasing Agent. It is preserved here as a discrete artifact for the evaluation committee's reference.

A.1 The GLP-1 number is the entire story

Addendum #2 disclosed three numbers that, together, reframe the entire proposal:

- 373 members are currently on GLP-1 medications through the County's medical plan

- 705 members used a GLP-1 in the past 12 months

- The County's only current GLP-1 cost-containment tool is OptumRx prior authorization

Three observations follow:

(a) The County is already spending heavily on GLP-1 medications. At the conservative unmanaged rate of $13,800/patient/year (RAND 2023), 373 current members represent approximately $5.15M per year in GLP-1 pharmacy spend with zero clinical wraparound.

(b) The 47% attrition rate is the smoking gun. 705 members started a GLP-1 in the past twelve months but only 373 are on therapy today. That ~47% discontinuation rate is consistent with published real-world GLP-1 adherence data and is the textbook signature of unmanaged GLP-1 therapy.

(c) The managed-protocol savings opportunity is approximately $2.09M per year. At RAND's conservative $5,600-per-patient savings differential, migrating the 373 current users captures approximately $2.09M annually — nearly funding the entire $1.71M Year-1 program cost.

A.2 The County has named its own incumbent strategy as insufficient

The Addendum states verbatim: "Current cost containment is tied to prior authorization program with PBM." The 47% attrition rate demonstrates that prior authorization alone is not converting pharmacy spend into outcomes. The Addendum further clarifies the County's preference: "A broader support-focused program centered around outcomes, health coaching participation, and sustainable lifestyle changes." The County explicitly rejected a compliance-focused program.

A.3 The County is buying program design, not administration

The Addendum confirms: "Recommend and design a comprehensive solution." The Addendum also confirms that either clinical model is acceptable: prescribing physicians on the vendor's staff OR NBHWC-credentialed coaches supporting members' own prescribers. Vitality offers both within a single integrated program — Dr. Love as the in-program prescribing lead, Dr. Vann's coaching model for members who stay with their existing PCP.

A.4 The eligible population is materially larger than typical estimates

| Metric | County figure |
| --- | --- |
| Total members enrolled (all ages) | 5,871 |
| Eligible adults (EE + dependents 18+) | 4,213 |
| Female share | 53% |
| Currently on GLP-1 | 373 (6.3% of enrolled) |
| Past-year GLP-1 users | 705 (12.0% of enrolled) |
| BMI ≥ 30 count | Unavailable from carrier |
| Modeled at-risk adults (CDC 36.2%) | ~1,525 |
| Target Vitality enrollment | 534 (35%) |
| Year-1 program cost (lifestyle baseline) | ~$1.71M |
| Status-quo annual cost of at-risk cohort | ~$4.02M/yr |

The Addendum's disclosure that "BMI ≥ 30 count: information unavailable through carrier" is significant. Any vendor claiming precise BMI-distribution-based outcome forecasts is bluffing — the source data does not exist within the carrier's reporting. Vitality's CDC PLACES anchored modeling is the only defensible approach.

A.5 The competitive landscape, fully visible

| Confirmed in Addendum #2 | Strategic implication |
| --- | --- |
| No incumbent weight-management vendor | True greenfield; no displacement story |
| Broker: IMA | IMA will be present at evaluation; partner, not gatekeeper |
| Wellness incumbent: Rally (via UHC) | We coexist; we do not replace |
| TPA: UnitedHealthcare (Group #902769) | Known integration surfaces; low risk |
| PBM: OptumRx | Standard pharmacy feeds available |
| No fixed budget; "focused on cost savings" | Value-based pitch wins |
| Virtual only | PWA-native; competitors with onsite are overspending |
| Adults 18+ | Simplified clinical scope |
| "Network access" = integration capability | Reframes as a Vitality strength |

A.6 The KPIs the County named, in order

- Continued member engagement — VITA AI persistent-memory advisor + Dr. Vann's behavioral cadence

- Proper use of GLP-1 medications — Dr. Love's clinical protocol with titration and adherence monitoring

- Cost savings — $2.09M GLP-1 capture + $675K medical + $282K productivity = $3.05M Year-1 opportunity vs. $1.71M cost

Notably absent: weight-loss percentages, BMI reduction targets, specific clinical biomarkers. The County views these as means, not ends. Vitality's reporting framework presents them as drivers of engagement, GLP-1 use, and savings — never as standalone metrics.

A.7 Procurement process facts

- Addendum #2 signed by Tammy Culley, Purchasing Agent — all communication routes through her

- Acknowledgment of Addendum #2 on the RFP response page is mandatory (see Appendix C)

- Deadline: 1:45 PM CDT, June 2, 2026; no late acceptance

Appendix B — Reconciled Numbers Source Sheet

Every numerical figure used in this proposal is drawn from one of three sources: (a) Sedgwick County RFP #26-0028 and its addenda, (b) peer-reviewed published research, or (c) Vitality's reconciled internal pricing and ROI model. The table below provides a single-page audit trail.

| Figure | Value | Source |
| --- | --- | --- |
| Total members enrolled on County plans | 5,871 | RFP #26-0028 Addendum #2 |
| Eligible adults (EE + dependents 18+) | 4,213 | RFP #26-0028 Addendum #2 |
| Female share | 53% | RFP #26-0028 Addendum #2 |
| Currently on GLP-1 | 373 | RFP #26-0028 Addendum #2 |
| Past-year GLP-1 users | 705 | RFP #26-0028 Addendum #2 |
| TPA | UnitedHealthcare (Group #902769) | RFP and Addendum #2 |
| PBM | OptumRx | RFP and Addendum #2 |
| Broker | IMA | RFP #26-0028 Addendum #2 |
| Wellness incumbent | Rally (via UHC) | RFP #26-0028 Addendum #2 |
| County obesity prevalence | 36.2% | CDC PLACES 2023 |
| Modeled at-risk adults | 1,525 | Derived: 4,213 × 36.2% |
| Target enrollment | 534 (35% of at-risk) | Vitality model; industry-standard voluntary uptake |
| Lifestyle pathway annual cost | $3,200/member/year | Vitality reconciled pricing |
| Blended PEPM (20% GLP-1 mix) | $476–$525 | Vitality reconciled pricing |
| GLP-1 unmanaged annual cost | $13,800/patient | RAND Corporation 2023 (conservative) |
| GLP-1 managed annual cost | $8,200/patient | RAND Corporation 2023 (conservative) |
| GLP-1 savings differential | $5,600/patient/year | Derived |
| Clinical success rate | 68% achieve ≥5% weight loss | NIH/DPP Trial |
| Per-success medical savings | $1,861/year | CDC / CMS 2023 |
| Per-success productivity savings | $778/year (2.73 days × $285/day) | RAND Corporation |
| Year-1 program cost (lifestyle baseline) | $1,708,800 | 534 × $3,200 |
| GLP-1 capture annual savings | $2,088,800 | 373 × $5,600 |
| Lifestyle + clinical annual savings | $957,957 | 363 × ($1,861 + $778) |
| Total Year-1 economic opportunity | $3,046,757 | Sum of above |
| Status-quo annual cost (at-risk cohort) | $4.02M/yr | 1,525 × $2,639 |
| Multi-year ROI Year 1 | 0.56x | Vitality model with graduate-savings carryover (85% retention, 3-year tail) |
| Multi-year ROI Year 3 | 1.01x | Vitality model |
| Multi-year ROI Year 5 | 1.32x | Vitality model |
| Harvard meta-analysis benchmark | $3.27 return per $1 | Health Affairs 2010 (upper-bound benchmark) |

Appendix C — Acknowledgment of Addenda

Pursuant to the County's instruction in Addendum #2 ("PLEASE ACKNOWLEDGE RECEIPT OF THIS ADDENDUM ON THE RFP RESPONSE PAGE"), the undersigned Prime Contractor formally acknowledges receipt of:

- Addendum #1 to RFP #26-0028 — received and incorporated into this response

- Addendum #2 to RFP #26-0028, issued May 22, 2026 by Tammy Culley, Purchasing Agent — received and incorporated into this response

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Eric Hargrave, CEO

Hargrave Innovative Solutions (Prime Contractor)

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Appendix D — Authorized Representative

The authorized representative for all matters relating to this proposal and any awarded contract is:

Eric Hargrave, CEO

Hargrave Innovative Solutions

ericd@hisolution.org

601-238-4186

All proposal questions, clarifications, contract negotiations, and post-award communications will be directed through this representative.

End of Proposal

Vitality Weight Management Program · Response to Sedgwick County RFP #26-0028

Submitted by Hargrave Innovative Solutions (Prime Contractor)

In partnership with Love Clinic MedSpa · Vanntastic Solutions · The COLLABORATIVE Advocate Foundation

June 2, 2026